# REQUEST FOR PROPOSALS (RFP)

# Community Wildfire Risk Assessment & Resiliency Plan

Town of Torbay and Town of Flatrock, Newfoundland and Labrador

## Introduction

The Town of Torbay and the Town of Flatrock, is seeking qualified proponents to undertake a comprehensive wildfire risk assessment and develop a Community Wildfire Resiliency Plan (CWRP). The overall purpose of this Project is to prepare a CWRP that incorporates SMART (strategic, measurable, achievable, relevant, and time-bound) goals and objectives that address the seven FireSmart disciplines (education, emergency planning, vegetation management, legislation, development, interagency cooperation, and cross-training).

Torbay and Flatrock are located within a wildland–urban interface (WUI) area characterized by:

- Dense boreal vegetation

- Expanding residential development

- Limited evacuation routes in certain neighbourhoods

- Increasing wildfire risk due to climate variability

This project supports municipal emergency preparedness, land-use planning, and public safety.

## Project Objectives

The successful proponent will:

### -Wildfire Risk Assessment

- Identify and map high-risk areas and neighbourhoods

- Analyze:

  - Vegetation/fuel types

  - Topography

  - Historical fire occurrence

  - Weather/climate trends

  - Structure density and construction types

- Develop a GIS-based wildfire risk model and maps

### -Community Wildfire Resiliency Plan

Develop a comprehensive plan aligned with FireSmart Canada principles and best practices, including:

- Hazard mitigation strategies for:

  - Municipal government

  - Residents and property owners

- Recommendations for:

  - Vegetation management

  - Fuel reduction zones

  - Firebreaks

- Infrastructure and emergency response improvements:

  - Water supply and hydrant access

  - Road access and evacuation routes

- Land-use planning and policy recommendations

- Public education and engagement strategy

## Scope of Work

The project shall include, at minimum:

### Phase 1: Data Collection & Review

- Review existing municipal plans, mapping, and policies

- Gather environmental and geospatial data

- Stakeholder consultation (fire department, municipal staff)

### Phase 2: Risk Assessment & Mapping

- Conduct WUI analysis

- Develop wildfire risk classification (e.g., low/moderate/high/extreme)

- Produce high-quality GIS maps and visual outputs

### Phase 3: Plan Development

- Draft Community Wildfire Resiliency Plan

- Incorporating SMART goals and objectives

- Address the 7 FireSmart disciplines

- Provide:

  - Short-term (1–3 years) actions

  - Medium-term (3–5 years) strategies

  - Long-term planning recommendations

### Phase 4: Engagement & Finalization

- Present draft findings to Council

- Incorporate feedback and deliver final report (in person or virtually)

## Deliverables

The proponent will provide:

- Wildfire Risk Assessment Report

- GIS datasets and high-resolution maps

- Community Wildfire Resiliency Plan (final report)

- Executive summary (public-friendly version)

- Presentation to Council and stakeholders (in person or virtually)

## Proponent Qualifications

Proposals should demonstrate:

- Experience in:

  - Wildfire risk assessment

  - WUI analysis

  - Community wildfire protection planning

- Familiarity with:

  - Canadian wildfire standards

  - FireSmart Canada guidelines

- Expertise in:

  - GIS and spatial modelling

  - Emergency management planning

- Previous municipal or government project experience

## Proposal Submission Requirements

Proposals must include:

- Company profile and relevant experience

- Proposed methodology and approach

- Project timeline and milestones

- Team qualifications

- Examples of similar completed projects

- Detailed pricing structure

“The final plan must align with provincial and federal wildfire resiliency funding program requirements and include implementation-ready actions with costing.”